## Milestones
Milestone Project
Project Name | PIC | Milestone Name |  | Target | Milestone Weighted |  |  | Milestone Achievement
|  |  |  | Date |  | May | Jun
Project RPA | Dev | Feasibility study |  | 2021-05-10 | 5% |  |  | 0%
Database
|  |  | Create Database Scheme | 2021-05-11 | 5% |  |  | 0% | rsg
| Dev | Basic Menu
|  |  | Authentication | May | 5% |  |  | 0% | rsg
|  |  | Authorization | May | 5% |  |  | 0%
| Dev | Master
|  |  | Data User | May | 8% |  |  | 0% | rsg
|  |  | Data RPA | May | 7% |  |  | 0%
|  |  | Data Area | May | 7% |  |  | 0%
|  |  | Data Item | May | 8% |  |  | 0%
| Dev | Tonase
|  |  | CRUD Tonase | Jun | 10% |  |  | 0% | rsg
|  |  | Report Tonase | Jun | 5% |  |  | 0%
| Dev | Produksi
|  |  | CRUD Produksi | Jun | 10% |  |  | 0% | rsg
|  |  | Report Produksi | Jun | 5% |  |  | 0%
| Dev | Penjualan
|  |  | CRUD Penjualan | Jun | 10% |  |  | 0% | mfn
|  |  | Report Penjualan | Jun | 5% |  |  | 0%
| All | UAT |  | 2021-07-11 | 5% |  |  | 0%
[5 empty] | 100% |  |  | 0%